## Sheet1
Concrete Deck Placement QC Checklist (Mar 2018) | Checkbox |  |  | COMMENTS
D#
Inspector - | Yes | No | N/A
QUALIFICATIONS
ACI Certification
REVIEW
Contract Plans
Contract Proposal
Standard Specifications Sections 501, 555 and 557
Construction Inspection Manual Sections 501, 555 and 557
Type of Concrete Specified (HP)
Air Content (6.5% desired, Range 5.0%-8.0%)
Slump Range (ex: 3in.-5in.)
Air Temperature 45 deg. F or Above
Placements September 15 to April 1-Engineer's Permission for cold-weather concreting
-Is approved heating plan on file if necessary?
Pre Placement Mtg. in accordance with 557-3.05
-Get site specific plan from contractor (pump location, washout area, work bridges, MPT, etc.)
-Get list of proposed manpower and equipment to be used
Check Placement Sequence for conformance with Plans
If No Bar List is shown in the Contract Documents, Contractor to Supply Bar List (557-3.17)
DRY RUN / PRIOR TO POUR
Check Formwork vs. Formwork Drawings
Check Reinforcing Bars-Size, Number and Spacing, cover/clearance
- Complete the rebar checklist?
Dry Run of Approved Finishing Machine-Check Grade, Cross-slope and Rebar Cover(557-3.07)
Verify Vertical Clear Distance (Top of Slab to Top Mat) within Tolerance + or - 1/2 in (557-3.16)
Turf Drag to be used on Approved List (557-3.07)
Have forms been oiled and hanger bolts greased
Have the forms been cleaned out
Have precast beams / adjacent concrete been prewetted
Concrete testing area established? Have wheelbarrow and tools necessary? Is cure box set up?
Is the burlap for the wet cure pre soaked? Water source and necessary hoses/sprinklers on site?
Concrete Placement
Is Standby equipment on site especially if pumping? also vibrators, generators, etc.
Is the workforce and equipment on site the same as proposed by the contractor at pre-pour mtg.?
Are the necessary materials/manpower on site to build temporary bulkhead if necessary?
Is the correct concrete mix being furnished? Correct friction stone?
Check Concrete Mixing Revolutions and Time Limits (Tables 501-6 & 501-7)
Check and Record Concrete Temperature
Test for Air Entrainment and Slump in accordance with Materials Method 9.2
Take Concrete Cylinders in accordance with Materials Method 9.2
- Additional cylinders may be needed if contractor requests early loading
Calculate Evaporation Rate using Figure 557-1
Conveyance of Concrete to be in accordance with 555-3.04B
Use One Insertion Vibrator for every 40 CY per hr. (Minimum of Two plus backups)
Vibrate Concrete in accordance with 555.3.04B
Cold Joints Placed in accordance with 557-3.06
Place Concrete using Finishing Machine (557-3.07)
Check Finished Concrete Surface using Straightedge (557-3.07)
Spot check rebar cover and deck thickness on deck behind finishing machine
Texture Surface using Turf Drag on Approved List (557-3.07)
Cover Concrete Surface with Clean, Prewetted Burlap (557-3.11)
Curing Period
Begin Curing Period only after all Concrete for the Placement is Complete (557-3.11)
Provide Continuous Uniform Wetting for the Entire Curing Period (14 Days)(557-3.11)
Monitor Curing Temperatures (between 45 deg. F and 85 deg. F) required (557-3.11)
Cold Weather Concrete -Maintain Curing Temps. For additional 14 Days (Drying Period) (557-3.12)
Spot Check Underside of Steel Forms by Sounding with a Hammer (557-3.13)
Remove section of Stay in Place Form to Examine Underside of Deck (557-3.13)
Form Removal in accordance with 555-3.09 and 555-3.13
Follow Requirements of 557-3.14 for Loading Limitations

## Sheet2
QUALITY CONTROL CHECKLIST
Bridge Deck Concrete Placement QC Checklist
CHECKBOX
REVIEW | YES | NO | N/A | COMMENTS
Contract Plans
Contract Proposal
Standard Specifications Sections 501, 555 and 557
Construction Inspection Manual Sections 501, 555 and 557
Type of Concrete Specified (HP)
Air Content (6.5% desired, Range 5.0%-8.0%)
Slump Range (ex: 3in.-5in.)
Air Temperature 45 deg. F or Above
Placements September 15 to April 1-Engineer's Permission for cold-weather concreting
-Is approved heating plan on file if necessary?
Pre Placement Mtg. in accordance with 557-3.05
-Get site specific plan from contractor (pump location, washout area, work bridges, MPT, etc.)
-Get list of proposed manpower and equipment to be used
Check Placement Sequence for conformance with Plans
If No Bar List is shown in the Contract Documents, Contractor to Supply Bar List (557-3.17)
DRY RUN / PRIOR TO POUR | YES | NO | N/A | COMMENTS
Check Formwork vs. Formwork Drawings
Check Reinforcing Bars-Size, Number and Spacing, cover/clearance
- Complete the rebar checklist?
Dry Run of Approved Finishing Machine-Check Grade, Cross-slope and Rebar Cover(557-3.07)
Verify Vertical Clear Distance (Top of Slab to Top Mat) within Tolerance + or - 1/2 in (557-3.16)
Turf Drag to be used on Approved List (557-3.07)
Have forms been oiled and hanger bolts greased
Have the forms been cleaned out
Have precast beams / adjacent concrete been prewetted
Concrete testing area established? Have wheelbarrow and tools necessary? Is cure box set up?
Is the burlap for the wet cure pre soaked? Water source and necessary hoses/sprinklers on site?
Concrete Placement | YES | NO | N/A | COMMENTS
Check Formwork vs. Formwork Drawings
Check Reinforcing Bars-Size, Number and Spacing, cover/clearance
- Complete the rebar checklist?
Dry Run of Approved Finishing Machine-Check Grade, Cross-slope and Rebar Cover(557-3.07)
Verify Vertical Clear Distance (Top of Slab to Top Mat) within Tolerance + or - 1/2 in (557-3.16)
Turf Drag to be used on Approved List (557-3.07)
Have forms been oiled and hanger bolts greased
Have the forms been cleaned out
Have precast beams / adjacent concrete been prewetted
Concrete testing area established? Have wheelbarrow and tools necessary? Is cure box set up?
Is the burlap for the wet cure pre soaked? Water source and necessary hoses/sprinklers on site?
Concrete Placement
Is Standby equipment on site especially if pumping? also vibrators, generators, etc.
Is the workforce and equipment on site the same as proposed by the contractor at pre-pour mtg.?
Are the necessary materials/manpower on site to build temporary bulkhead if necessary?
Is the correct concrete mix being furnished? Correct friction stone?
Check Concrete Mixing Revolutions and Time Limits (Tables 501-6 & 501-7)
Check and Record Concrete Temperature
Test for Air Entrainment and Slump in accordance with Materials Method 9.2
Take Concrete Cylinders in accordance with Materials Method 9.2
- Additional cylinders may be needed if contractor requests early loading
Calculate Evaporation Rate using Figure 557-1
Conveyance of Concrete to be in accordance with 555-3.04B
Use One Insertion Vibrator for every 40 CY per hr. (Minimum of Two plus backups)
Vibrate Concrete in accordance with 555.3.04B
Cold Joints Placed in accordance with 557-3.06
Place Concrete using Finishing Machine (557-3.07)
Check Finished Concrete Surface using Straightedge (557-3.07)
Spot check rebar cover and deck thickness on deck behind finishing machine
Texture Surface using Turf Drag on Approved List (557-3.07)
Cover Concrete Surface with Clean, Prewetted Burlap (557-3.11)
Curing Period | YES | NO | N/A | COMMENTS
Begin Curing Period only after all Concrete for the Placement is Complete (557-3.11)
Provide Continuous Uniform Wetting for the Entire Curing Period (14 Days)(557-3.11)
Monitor Curing Temperatures (between 45 deg. F and 85 deg. F) required (557-3.11)
Cold Weather Concrete -Maintain Curing Temps. For additional 14 Days (Drying Period) (557-3.12)
Spot Check Underside of Steel Forms by Sounding with a Hammer (557-3.13)
Remove section of Stay in Place Form to Examine Underside of Deck (557-3.13)
Form Removal in accordance with 555-3.09 and 555-3.13
Follow Requirements of 557-3.14 for Loading Limitations