## Sheet2
QUALITY CONTROL CHECKLIST
PILE INSTALLATION CHECKLIST
CHECKBOX
Pre Operation Review | YES | NO | N/A | COMMENTS
Construction Tolerances for the piles being driven
a) Vertical Piles being driven
b) Battered Piles being driven (check that batter of pile is within tolerance)
Profile where the piles are to stop and in what material
Boring Logs
Foundation Report
Form BD-138 (Pile Driving Equipment and Criteria) Approved by D.C.E.S.
Memo that accompanies BD-138 (from Structures)
Special Pile Coatings required
Criteria for accepting piles(e.g. length,rated resistance, refusal)
GEM-26 Pile Driving Inspection Manual
Standard Specifications Sections 551, 552 and 564
Construction Inspection Manual Sections 551, 552 and 564
Basic Inspection of Construction-Pages 73-84
Steel Construction Manual Subsections 302,306,704 and 811
PILE DRIVING FIELD INSPECTION | YES | NO | N/A | COMMENTS
Material Certification
Piles are straight and of proper size,length and weight for compliance with contract
Check pile for damage prior to driving
Prefabricated or commercial pile shoes as detailed on the plans or as approved by D.C.E.S.
Pile Shoes attached in accordance with WPS (approved by D.C.E.S.) and SCM
Pile Splicing done inaccordance with WPS (approved by D.C.E.S.) and SCM
Welding done by NYSDOT Certified Welder
Welding parameters are followed,including preheating and drying electrodes prior to their use
Check that excavation is at grade
Inspect Pile Hammer
Check that pile marked every foot
Check that pile marked every inch near the estimated length
H-Piles-Make sure that orientation is correct
Establish reference for monitoring pile penetration
Tip elevation verified
Cutoff elevation verified
Pile penetration verified
Pile driven to driving criteria
Pile driven to minimum tip penetration
Pile driven to refusal
Record final blow counts
Driving Irregularities identified
Pay quantities identified
Record length of pile for payment
Record time the driving stopped
Driving Resistance recorded
Record Piles | YES | NO | N/A | COMMENTS
a) Record Piles determined by EIC(e.g. 2 piles per structure per stage,one pile in every 10)
b) Record blow counts for entire length
Contract Documents require that heave is to be monitored | YES | NO | N/A | COMMENTS
a)Pile Top surveyed and elevation noted
b)One ft. of pile left above cutoff for possible restriking
Cast-In-Place Piles (post driving) | YES | NO | N/A | COMMENTS
a)Pile Top covered to keep out water and debris
b)pile is internally inspected
c)Concreting done in accordance with the Specifications
Pile Testing | YES | NO | N/A | COMMENTS
Dynamic Pile Testing
Static Load Tests
Pile Information sent to D.C.E.S. for final approval
Pile Table in Contract Plans completed as part of As-Built Plans