## Sheet1
Concrete Formwork Checklist
Falsework and Forms |  |  | Comments
After erection of beams and before falsework or forms for bridge decks are set, elevations are to be checked at the top of beams.
Forms are to be built strong, stable, firm, mortar-tight, and adequately braced or secured.
Forms are to be made of wood, steel, or other approved material.
Forms are to be clean and clear of all debris.
Forms are to be treated with form oil or other approved release agent before reinforcing steel is placed or self-releasing forms used. Note: Release agents that adhere to or discolor concrete cannot be used.
Working drawings should also include sequence, method, and rate of placement of concrete.
Written installation procedures from the manufactureer need to be provided for clips, braces, hangers, and other manufactured parts.
Falsework and forms are to be built to withstand all loads and pressures, including stresses due to the rate of placement and effect of vibrations.
Forms are to be constructed to compensate for variations in camber of supporting members and allow for deflections.
All sharp corners are to be grooved joints as specified on the plans.
When removed, forms are not to leave any irregular projections, or cavities.
Forms have to produce a smooth surface of uniform texture, free of voids, indentations, protrusions, and bulges for concrete surfaces exposed to view.
Panels for form-liners are to have joint lines form a symmetrical pattern conforming to general lines of the structure.
The same type of pattern for form-liners need to be used throughout each element of structure.
Forms are to be rigid enough so exposed surface does not have a wave-like appearance that exceeds 1/4 inch when checked with a 4-foot straightedge.
Forms are to be rigid enough so non-exposed surface does not exceed 1/2 inch when checked with a 4-foot straightedge. (i.e. back side of retaining wall, bridge footing, etc.)
Forms are to be constructed so that metal ties and anchors can be removed to a depth of at least 2 inches without damaging concrete.
When coated reinforcing steel (i.e. epoxy, galvanized, etc.) is required, metal ties, anchorages, and spreaders need to be of corrosion-resistant material or coated with a non-conducting material.
The date when the superstructure is completed must be cast in at least two places as noted on the plans.
Deck forms for bridges are to be supported directly on girders so that no differential settlement of the forms occurs during placing of the concrete.
Working drawings for stay-in-place metal forms for bridge decks submitted for review and approval by the Engineer shall include:
method of construction
erection and placement plans
attachment details
weld procedures
material lists
material designation
gauge of all materials
details of corrugation
form design and computations
Stay-in-place form hangers are to be attached to the top flanges of beams or girders.
Stay-in-place metal forms are not used where longitudinal slab construction joints are located, under cantilevered slabs, and bridges over a salt-laden body of water with less than 15 feet clearance. If not on plans, send an Engineering Clarification Memo
Welding to top flanges of steel beams and girders in tension is not permitted. Any welding on top flanges must be approved by the Engineer.
CAUTION: Drilling of holes in or the use of power-actuated tools on pre-stressed concrete beams for fastening supports is not permitted.
Welding of reinforcing steel to pre-stressed units is not permitted.
Stay-in-place metal forms are to be unloaded, stored 4 inches above ground, and protected against corrosion and damage.
Flame cutting of forms is not permitted. Approved cuts shall be treated as approved by the Engineer.
Welding of forms to supports is not permitted.
Steel form supports should be placed directly on floor beam flanges and attached by bolts, clips, welding where permitted, or other means.
Forms are to be securely fastened to form supports with self-drilling fasteners at a maximum spacing of 18 inches and should have a minimum bearing length of 1 inch at each end.
Where form sheets lap, they are to be securely fastened by fasteners at a maximum spacing of 18 inches.
No part of the forms or their supports are to protrude into the slab.
All reinforcement in the bottom reinforcement mat is to have a minimum concrete cover of 1 inch or as specified on plans.
When forming construction joints, all loose and foreign material is to be removed and the surface roughened and thoroughly wet with water.
All reinforcing steel can be extended continuously through joints as noted on plans.
Open joints are to be formed by the insertion and removal of templates of wood, metal, or other suitable material.
Filled joints are to be made with joint filler as specified on the plans.
The openings to accommodate pipe, conduit, and utility installations are to be incorporated into formwork.
The anchor bolts and systems are to be installed prior to placing concrete.
Grouted anchors are to be installed into drilled or formed holes suitable to receive them.
Holes shall be perpendicular to the plane surface and be located to avoid damage to existing reinforcement.
Ornamental molds used are to be coated with a form release agent to prevent adherence to concrete.
Falsework and forms are to be removed in manner to permit the structure to uniformly and gradually take the stresses of it own weight.
Removal shall be controlled by field-cured cylinder tests and are not to begin until the concrete has achieved 75% of the design compressive strength.
A pour sequence should be defined on the plans for bridge decks. If not, an ECM should be sent to the Lead Engineer.
If any TPCBC is moved to create access for the concrete delivery, forms should be re-inspected for shifting. Notify Contractor to recheck formwork braces.